## Sheet1
TASK SHEET
Day | Thứ 7 - 23/05/2015 | Chủ nhật - 24/05/2015 | Thứ 2 - 25/05/2015 | Thứ 3 - 26/05/2015 | Thứ 4 - 27/05/2016 | Thứ 5 - 28/05/2016 | Thứ 6 - 29/05/2015 | Thứ 7 - 30/05/2015 | Chủ nhật - 31/05/2015 | Thứ 2 - 01/06/2015
Mai | - HTML searchProject.jsp - HTML projectDetail.jsp - HTML add engineer to project screen.jsp |  | Review & update use case, class diagram, database | - HTML CreateProject.jsp - HTML SearchAccount.jsp ( View, Edit) - HTML CreateAccount.jsp - Review ERD | - Review Usecase, ERD, Class Diagram | - Code Search/View Account - Code Edit Account. | - Code Create Account | - Code Search/View Employee - Code View Employee Detail - HTML SearchRecruitment.jsp - Code View/ Search Recruitment
Phước |  |  | Review & update use case, class diagram, database | update use case, erd | update use case, erd, class diagram | -Support Mai | -Interview Mr Hien - bu leader of fsu 11 -Code addTimesheet function: 50% -Support Mai to code addAccuount function | -Support Mai -Code addTimesheet function: 90% | -Code addTimesheet : done -Code update/delete/show: timesheet: done | -Code reviewTimesheet: 80%
Kiện | -HTML feedback.jsp, appraisal.jsp |  | -Review và sửa Usecase diagram, ERD -Review database, class diagram |  | - update erd, class diagram | - Sua lai use case, ERD, class diagram | - Gap anh Hien - code html listCriterion.jsp (80%) | - hoan thanh html listCriterion.jsp - code CriterionDAO; CriterionDTO - List/ Add/Edit/Remove Criterion Servlet | - fix javascript bi loi | - Sua lai erd va class diagram theo huong database - Hoan thanh chuc nang List/ Add/ Edit/Remove Appraisal Criterion
Hoàng | -Không có sản phẩm, support là chính | -Apply phân trang vào các page searchEmployee -Hoàn thiện các trang searchKnowledge, knowledgeDetail, projectDetail -Learning localStorage -Review ERD, database, 2 class diagram | -Review và update 4 diagram | -HTML CreateKnowledge.jsp -Review và update usecase, ERD | -Review 4 diagram, viết common.java để chuẩn bị code back-end | -Fix database, code back-end/front-end cho searchProject.jsp, ListAllProject cho role Engineer, Manager, Director (vẫn còn Customer chưa xong) | -Supporting -Learning algorithm, prepare SQL for suggest system | -Support code front-end/back-end -Support code back-end of Recruitment function -Support ERD | -Code project detail (function view project detail, all member, role) -Tab knowledge, evaluate function, Edit function, Suggest system left -Change database some locations | -Code project detail (function edit project) -Support Recruitment flow, Criterion flow -Review erd and class diagram, usecase, database